## Sprint_Plan
Sprint | Task ID | Task Description | Assigned To | Start Date | End Date | Status | Remarks
Sprint 1 | T1 | Requirement Analysis and PRS preparation | Team | 2025-01-01 | 2025-01-03 | Completed | Aligned with Firebase Studio
Sprint 1 | T2 | UI and Wireframe Design using Figma | Team | 2025-01-02 | 2025-01-05 | Completed | Approved design
Sprint 2 | T3 | Firebase Studio Project Setup | Developer | 2025-01-06 | 2025-01-07 | Completed | Hosting and Firestore configured
Sprint 2 | T4 | Frontend Implementation | Developer | 2025-01-07 | 2025-01-10 | Completed | Core UI functional
Sprint 3 | T5 | Meal Builder Logic Implementation | Developer | 2025-01-11 | 2025-01-13 | Completed | Rule based logic
Sprint 3 | T6 | Nutrition Analysis Implementation | Developer | 2025-01-13 | 2025-01-15 | Completed | Predefined data aggregation
Sprint 4 | T7 | Session History Integration | Developer | 2025-01-16 | 2025-01-17 | Completed | Firestore based
Sprint 4 | T8 | Testing and Bug Fixes | QA | 2025-01-18 | 2025-01-19 | Completed | No major defects
Sprint 5 | T9 | Documentation Preparation | Team | 2025-01-20 | 2025-01-22 | Completed | PRS, Design, Test docs
Sprint 5 | T10 | Deployment and Demo Preparation | Team | 2025-01-23 | 2025-01-24 | Completed | Firebase Hosting live